## Instructions
Chemical supplier approval document register
One row per document per customer request. Fill the Register sheet; the Example sheet is illustrative only.
1. Before opening any file, list every document the customer request names: Document, Requirement it meets, Placement.
2. Copy Issuer, Issue or revision date and Expiry date from the document itself, not from a file name or email.
3. Dates as YYYY-MM-DD. Write none in Expiry date where the document has no expiry, and keep its revision date.
4. Validity remaining (days) = Expiry date minus Planned submission date. Enter dates as dates and it calculates.
5. State is present, missing, expired or unapproved (unsigned, draft, or not released by the issuer).
6. Choose one reference document (request or TDS). Copy product name, grade, part number, lot and revision as printed on each document, then note any that differ.
7. Every missing, expired or unapproved document and every blocking mismatch gets a Fix, one Owner and a Due date.
8. Ready to submit only when no required row is missing, expired, unapproved or in conflict. Earliest submission date = latest Due date among rows with Blocks submission = yes.
The CSV file in the same download has the Register header row only, UTF-8, for tools that import CSV but not Excel.
Template from www.lubinpla.com/post/chemical-supplier-approval-document-checklist

## Register
Customer request reference | Product name (as on request) | Document | Requirement it meets | Placement (required/conditional/not required) | Issuer (legal entity, site) | Issue or revision date (YYYY-MM-DD) | Expiry date (YYYY-MM-DD or none) | Planned submission date (YYYY-MM-DD) | Validity remaining at submission (days) | State (present/missing/expired/unapproved) | Product name on document | Grade on document | Part number on document | Lot on document | Revision on document | Mismatch (identifier, value A / value B) | Fix | Owner | Due date (YYYY-MM-DD) | Blocks submission (yes/no) | Closed date (YYYY-MM-DD)

## Example (illustrative)
ILLUSTRATIVE EXAMPLE. Values describe no real product, supplier or customer.
Customer request reference | Product name (as on request) | Document | Requirement it meets | Placement (required/conditional/not required) | Issuer (legal entity, site) | Issue or revision date (YYYY-MM-DD) | Expiry date (YYYY-MM-DD or none) | Planned submission date (YYYY-MM-DD) | Validity remaining at submission (days) | State (present/missing/expired/unapproved) | Product name on document | Grade on document | Part number on document | Lot on document | Revision on document | Mismatch (identifier, value A / value B) | Fix | Owner | Due date (YYYY-MM-DD) | Blocks submission (yes/no) | Closed date (YYYY-MM-DD)
REQ-0001 (illustrative) | Grade 40 | SDS | REACH Article 31; customer request item 1 | required | Producing site | 2026-03-12 | none | 2026-11-10 |  | present | Grade 40S | 40S |  |  | 2026-03-12 | Product name: Grade 40S / Grade 40 | Reissue SDS with product name Grade 40 | Regulatory affairs | 2026-11-06 | yes
REQ-0001 (illustrative) | Grade 40 | TDS | Customer specification | required | Producing site | 2025-09-01 | none | 2026-11-10 |  | present | Grade 40 | 40 |  |  | Rev 3 | Reference document |  |  |  | no
REQ-0001 (illustrative) | Grade 40 | CoA | Customer specification | required | Plant laboratory | 2026-10-14 | none | 2026-11-10 |  | present | Grade 40 | 40 |  | 2610-014 | [5 empty] | no
REQ-0001 (illustrative) | Grade 40 | ISO 9001 certificate | ISO 9001 clause 8.4 | required | Certification body | 2024-06-01 | 2027-05-31 | 2026-11-10 | 202 | present |  |  |  |  | ISO 9001:2015 |  |  |  |  | no
REQ-0001 (illustrative) | Grade 40 | REACH SVHC statement | Customer request item 5 | conditional | Regulatory affairs | 2025-08-20 | none | 2026-11-10 |  | expired | Grade 40 | 40 |  |  |  | Older than the customer's 12-month rule (illustrative rule) | Reissue against the current Candidate List | Regulatory affairs | 2026-11-05 | yes
REQ-0001 (illustrative) | Grade 40 | RoHS statement | Directive 2011/65/EU Annex II | conditional | Quality department |  | none | 2026-11-10 |  | unapproved | Grade 40 | 40 |  |  | Draft | Unsigned draft | Sign and date | Quality manager | 2026-11-03 | yes
REQ-0001 (illustrative) | Grade 40 | Customer questionnaire | Customer's own form | required | Technical service | 2026-10-20 | none | 2026-11-10 |  | present | Grade 40 | 40 | [7 empty] | no