## Instructions
OEM lubricant approval tracker
Template from www.lubinpla.com/post/oem-lubricant-approval-tracker-template
What it is for: one row per test that one OEM specification requires, showing whether a valid report exists, whether it meets the limit, and what is still needed.
1. Specification pass: from the OEM's current specification revision, fill Row ID to Limit for every test. Leave result columns blank.
2. Report pass: for each row, find the report with the same method, edition and conditions. Fill Our result to Formulation code submitted.
3. State pass: set State for every row. For 'not counted', pick one Reason not counted. For every row not 'met', fill Action, Action owner and Due date.
4. Approval status: only 'OEM listed' when Approval evidence names an OEM letter, licence number or OEM list revision. 'Meets the specification' is 'self-declared meets'.
5. Gap list: filter State on 'not met', 'missing' and 'not counted'.
6. Before submission, a second person repeats the report pass against the original reports.
Units: write values with units in the cell, as the column header shows (°C, h, rpm, bar, load stage, mm2/s).
Pick lists: State, Reason not counted, Approval status and Laboratory approved by OEM use drop-down lists (see sheet Lists).
CSV: the CSV file has the same columns as sheet Tracker. Save Tracker as CSV (UTF-8) to load records into systems that do not read .xlsx files.
Sheet Example is illustrative. Its values describe no real product, report, laboratory or approval.
Limits: the OEM's own approval procedure decides what is tested, where, and how long a listing lasts. This tracker records evidence; it does not grant approval.
Submission record (fill before submitting this tracker to the OEM):
Submission and recipient OEM:
Overall state (ready to submit / needs remediation):
Earliest submission date (YYYY-MM-DD):

## Tracker
Row ID (number) | OEM | Specification code | Specification revision (rev or YYYY-MM-DD) | Specification source (page, table, clause) | Test item | Test method and edition | Test conditions (°C; h; rpm; bar; load stage) | Limit (value and unit) | Our result (value and unit) | Report reference | Report date (YYYY-MM-DD) | Laboratory | Laboratory approved by OEM (Yes/No/Not required/Unknown) | Formulation code tested (code, revision) | Formulation code submitted (code, revision) | State (met/not met/missing/not counted) | Reason not counted (pick list) | Approval status (pick list) | Approval evidence (OEM letter, licence number, list revision) | Action | Action owner (person or role) | Due date (YYYY-MM-DD) | Notes

## Example
EXAMPLE (ILLUSTRATIVE): values describe no real product, report, laboratory or approval.
Row ID (number) | OEM | Specification code | Specification revision (rev or YYYY-MM-DD) | Specification source (page, table, clause) | Test item | Test method and edition | Test conditions (°C; h; rpm; bar; load stage) | Limit (value and unit) | Our result (value and unit) | Report reference | Report date (YYYY-MM-DD) | Laboratory | Laboratory approved by OEM (Yes/No/Not required/Unknown) | Formulation code tested (code, revision) | Formulation code submitted (code, revision) | State (met/not met/missing/not counted) | Reason not counted (pick list) | Approval status (pick list) | Approval evidence (OEM letter, licence number, list revision) | Action | Action owner (person or role) | Due date (YYYY-MM-DD) | Notes
1 | Pump maker A (illustrative) | Fluid spec 123 | Rev 4, 2026-03-02 | Table 2, row 1 | Pump break-in | OEM pump test procedure | 10 h; 250 bar; 60 °C | No failure | Passed | LAB-2026-0301 | 2026-03-01 | Neutral laboratory B | Yes | HLP46-F3 | HLP46-F3 | met |  | submitted | Not yet issued | None | Approvals manager |  | Illustrative row
2 | Pump maker A (illustrative) | Fluid spec 123 | Rev 4, 2026-03-02 | Table 2, row 3 | Pump corner power test | OEM pump test procedure | 200 h; 500 bar; 100 °C | No failure | Passed at 350 bar | LAB-2025-1120 | 2025-11-20 | Neutral laboratory B | Yes | HLP46-F3 | HLP46-F3 | not counted | conditions differ | submitted | Not yet issued | Rerun at 500 bar | Laboratory lead | 2026-12-15 | Illustrative row
3 | Pump maker A (illustrative) | Fluid spec 123 | Rev 4, 2026-03-02 | Table 3, row 2 | FZG scuffing | ISO 14635-1:2023 | A/8,3/90 | Failure load stage 10 or higher | Stage 12 | LAB-2024-0510 | 2024-05-10 | Neutral laboratory C | Yes | HLP46-F2 | HLP46-F3 | not counted | other formulation | submitted | Not yet issued | Ask OEM in writing whether F2 result carries over | Approvals manager | 2026-11-30 | Illustrative row
4 | Pump maker A (illustrative) | Fluid spec 123 | Rev 4, 2026-03-02 | Table 3, row 6 | Air release | Method named in specification | Conditions from specification | Limit from specification |  |  |  |  | Unknown |  | HLP46-F3 | missing |  | not started |  | Plan test | Laboratory lead | 2026-12-01 | Illustrative row

## Lists
State | Reason not counted | Approval status | Laboratory approved by OEM
met | conditions differ | OEM listed | Yes
not met | method edition differs | self-declared meets | No
missing | other formulation | submitted | Not required
not counted | laboratory not approved | not started | Unknown
past validity
contradicts another document